## Sheet1
Project Ref. No 1 |  | Project Title |  | Activity Plan Prepared By |  | Date of Preparation of Activity Plan
Sr. No | Task | [5 empty] | Start Date | End Date | Actual Days | Member’s name | Status
CRS document
1 | Introduction |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
2 | Existing Scenario |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
3 | Customer Requirement Specification |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
4 | Functional Requirement Specification |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
5 | System Requirements |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
6 | Development Software |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-17 | 2017-09-22 | 5 | All of Team | FINISH
Use Case and Sequence Diagrams
7 | Guest register as Reader |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
8 | Guest Login as Reader |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
9 | Guest Login as Journalist |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
10 | Journalist create article |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
11 | Journalist edit article |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
12 | Guest login as Editor |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
13 | Editor search article |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
14 | Editor change article status |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
15 | Editor manage comments |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
16 | View information |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
17 | Edit Information |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
18 | Change password |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
19 | Write new comment |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
20 | Change own comment status |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
21 | View article |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
22 | Search article by title |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
23 | Find article by categories |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
24 | Login as admin |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
25 | View accounts list |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
26 | Search account by username |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
27 | Change account role |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
28 | Change account status |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
29 | Logout |  | 24H Website |  | V.X.M. Tuấn |  | 2017-09-22 | 2017-09-22 | 1 | V.X.M. Tuấn | FINISH
ERD
30 | Conceptual |  | 24H Website |  | T.L.G. Luật |  | 2017-09-24 | 2017-09-24 | 1 | T.L.G. Luật | FINISH
31 | Logical |  | 24H Website |  | T.L.G. Luật |  | 2017-09-24 | 2017-09-24 | 1 | T.L.G. Luật | FINISH
32 | Tables |  | 24H Website |  | T.L.G. Luật |  | 2017-09-24 | 2017-09-24 | 1 | T.L.G. Luật | FINISH
33 | Database Relationship |  | 24H Website |  | T.L.G. Luật |  | 2017-09-24 | 2017-09-24 | 1 | T.L.G. Luật | FINISH
34 | Table Definition |  | 24H Website |  | T.L.G. Luật |  | 2017-09-24 | 2017-09-24 | 1 | T.L.G. Luật | FINISH
GUI
35 | Site map |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
36 | Home page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
37 | Login pop-up |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
38 | Search result page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
39 | Register pop-up |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
40 | Category page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
41 | Article page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
42 | Footer and comments |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
43 | Term and policy page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
44 | About us |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
45 | Profile page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
46 | Edit profile pop-up |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
47 | Change password pop-up |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
48 | Manage Article page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
49 | Create, edit article |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
50 | Censor articles page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
51 | Admin home page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
52 | Search account page |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
53 | Change role pop-up |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
54 | Account detail |  | 24H Website |  | D.A. Tuấn |  | 2017-09-22 | 2017-09-27 | 1 | D.A. Tuấn | FINISH
Test case
55 | Login |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
56 | Register |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
57 | Create Article |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
58 | Edit Article |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
59 | Search article (editor) |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
60 | Change article status |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
61 | Change comment status |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
62 | View own profile |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
63 | Edit own profile |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
64 | Change password |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
65 | Create new comment |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
66 | Change comment status |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
67 | Read article |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
68 | Search article by title |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
69 | Search article by category |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
70 | View account list |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
71 | Search account by username |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
72 | Change user role |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
73 | Change user status |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
74 | Logout |  | 24H Website |  | T.L.G. Luật |  | 2017-09-28 | 2017-09-29 | 1 | T.L.G. Luật | FINISH
Task sheet
75 | Task sheet |  | 24H Website |  | D.A. Tuấn |  | 2017-09-17 | 2017-10-21 | 1 | D.A. Tuấn | FINISH